SITUATION REPORT – PARK PLACE CENTER

UPDATE: 1800 HRS 29MAR20

RISK: MODERATE

SITUATION: STABLE

SITUATION UPDATE

- Facility reports a 4th symptomatic patient was transported to the hospital.

- Facility staff has followed up with the families of the (4) previously transported residents and report all show improvements and report no fever; treatment includes IVABT with O2.

- SB OEM coordinating development of a relocation plan using lessons from the recent relocation of the Woodbridge care facility.

RELOCATION PLANNING

- Facility will request relocation due to staff shortage with the following criteria;

  - Dietary and housekeeping staff shortage of 30% including consideration for backfilling positions with other staff and the inability to outsource needs.

  - Nursing staff shortage of 40% to include consideration for backfilling from sister agencies.

  - Nursing assistant staff shortage of 40% and unable to backfill positions with alternative staff.

- The notification for relocation is at the direction of leadership with Genesis Corporation.

SBOEM PLANNING - non-emergent relocation of residents.

  - The Township is coordinating a pre-plan for the relocation of residents that will trigger at 60% of above staff shortages.  It is expected that the 60% metric will provide for 48-72 hours of coordination.

  - Middlesex County EOC ESF-8 is developing the pre-plan for a NJ OEM resource request from the county volunteer medical reserve corp.  The resource request is via NJOEM E-Team and anticipate a 2-3-day lead for resources on scene.

END UPDATE

SITUATION REPORT – PARK PLACE CENTER

REPORT 27MAR20

Genesis Corporation

Park Place Center Care Facility

2 Deer Park Drive

Monmouth Junction, NJ

RISK: MODERATE

SITUATION: STABLE

Genesis Corporation

Park Place Center Care Facility

2 Deer Park Drive

Monmouth Junction, NJ

FACILITY CONTACTS

Facility 732 274 1122

Administrator Jennifer, cell 609 874-6034

Director of Nursing, Armit Kaur, cell 609 874 4911 (backup Administrator)

Director Infectious Disease, Nellicent Haggan, 732 236-4056

BACKGROUND

On 27 March, facility contacted Township to report the impact of COVID-19 on facility.  Facility is practicing infectious disease protocols to include patient isolation and PPE.

The Park Place Care Facility provides short and long term care for medical and memory impaired patients.

- The facility has two distinct care areas

  - Short and long term medical care "Terrace Wing” with a (44) resident capacity and occupied with (40) residents as of 27 Mar

  - Memory care “Garden wing” with (50) bed capacity and occupied with (45) residents as of 27 Mar.

  - Occupied with (85) residents as of 27 Mar

  - Roster of 76 staff providers

SITUATION

- (3) residents COVID-19 symptomatic and transported to local hospital with low grade fever

  - COVID-19 test administered with results expected Sunday

- (3) staff symptomatic and off site in self quarantine

  - Receptionist last worked 3/24 and called out sick on 3/25 reporting cold like symptoms

    - Not tested for COVID-19; did not meet criteria

  - Nurse Director of Memory Care unit was tested on arrival for work on 3/24 and sent home with low grade fever

    - Tested for COVID-19 await result

  - Nurse Assistance of short/long term care unit was tested on arrival to work on 3/24 and sent home with low grade fever.

    - Assessed by local physician on 3/25 with normal temp

- Facility has requested additional staff from a nursing temp agency.

- PPE Supplies

  - Adequate supply of masks and gowns

  - Short on face shields and googles.

    - Corporate office delivering 7 day supply of reusable (2) masks and goggles expected to arrive the evening of 27 Ma

  - Township of Plainsboro notified for EMS awareness

NEXT STEPS

- Requesting additional air gap thermometers, back ordered with delivery expected in late April

- Administrator to review staffing charts to determine minimal operational staffing levels and staff count to trigger for critical action.

  - Will determine 48-72 hour metric to trend staff levels near critical action.

- Administration to consult with Corporate staff to determine the number of symptomatic patients required to activate evacuation protocols.

- Administrator to contact predetermined transfer facilities and ascertain ability to absorb symptomatic patients.

- Notification to Township of Plainsboro for EMS awareness, complete 27 Mar